## Version History
Metrics Analysis Report - Development Projects v 1.2
| Sl. No. | Version No | Date | Prepared by | Reviewed by | Reviewed On | Approved by | Approved on | Change Details
| 1 | 1.1 | 2018-10-10 | Nagoor Inaganti | Nagoor Inaganti | 2018-10-15 | Nagoor Inaganti | 2018-10-10 | Iteration 1
| 2 | 1.2 | 2018-11-05 | Nagoor Inaganti | Nagoor Inaganti | 2018-11-20 | Nagoor Inaganti | 2018-11-20 | Iteration 2
Classification: TANVIIT¦ CONFIDENTIAL/INTERNAL/PUBLIC
Copyright Information The information contained in this document is the exclusive property of TanviIT Solutions Inc. This Project /Work is protected and no part of this Project /Work may be reproduced or transmitted in any form or by any means, electronic or mechanical, including photocopying and recording, or by any information storage or retrieval system, except as expressly permitted in writing by TanviIT Solutions Inc.

## Project Profile
Metrics Analysis Report - Development Projects v 1.2
Project Name | Red Turf
Project Code | RT 001
Team Lead | Monalisha Mishra
Project Manager | Nagoor Inaganti
Project Start Date | 2018-10-01
Project tentative end date | 2019-04-03

## Effort Metrics
Metrics Analysis Report - Development Projects v 1.0
EFFORT VARIANCE
Ver. or Release No. / Phases | Planned Effort (Person days) | Revised Planned Effort (Person Days) | Actual Effort (Person Days) | %variance against planned | %Variance against Revised planned
Iteration-1 | Search
Requirements | 3 | 2 | 3 | -33.33% | 50%
Requirements Review | 2 | 2 | 2 | 0% | 0%
Requirements Rework | 4 | 3 | 3 | -25% | 0%
Design | 42 | 44 | 44 | 4.762% | 0%
Design Review | 2 | 2 | 2 | 0% | 0%
Design Rework | 12 | 10 | 10 | -16.67% | 0%
Coding | 8 | 7 | 7 | -12.5% | 0%
Code Review | 1 | 1 | 1 | 0% | 0%
Code Rework | 2 | 2 | 3 | 0% | 50%
Unit Testing | 3 | 3 | 3 | 0% | 0%
Unit test case Review | 1 | 1 | 1 | 0% | 0%
Test case Design | 3 | 3 | 3 | 0% | 0%
Test case Review | 1 | 2 | 2 | 100% | 0%
Test case Rework | 1 | 1 | 1 | 0% | 0%
Testing | 2 | 3 | 3 | 50% | 0%
Acceptance | 1 | 1 | 1 | 0% | 0%
Support | 1 | 1 | 1 | 0% | 0%
Project Management | 8 | 9 | 8 | 12.5% | -11.11%
PPQA (Audits) | 2 | 2 | 1 | 0% | -50%
Risk Mgmt | 1 | 1 | 1 | 0% | 0%
Config Mgmt | 1 | 1 | 1 | 0% | 0%
Others (DAR, Analysis & Resolution, Misc) | 2 | 2 | 2 | 0% | 0%
Effort Variance for Iteration No: <1> | 103 | 103 | 103 | 0.79762 | 0.38889
Iteration No. <<2>> | Email
Requirements | 3 | 3 | 3 | 0% | 0%
Requirements Review | 2 | 3 | 2 | 50% | -33.33%
Requirements Rework | 4 | 3 | 3 | -25% | 0%
Design | 37 | 34 | 36 | -8.108% | 5.882%
Design Review | 2 | 2 | 2 | 0% | 0%
Design Rework | 12 | 12 | 12 | 0% | 0%
Coding | 8 | 7 | 7 | -12.5% | 0%
Code Review | 1 | 2 | 1 | 100% | -50%
Code Rework | 2 | 2 | 2 | 0% | 0%
Unit Testing | 5 | 3 | 3 | -40% | 0%
Unit test case Review | 1 | 2 | 1 | 100% | -50%
Test case Design | 3 | 3 | 3 | 0% | 0%
Test case Review | 5 | 6 | 5 | 20% | -16.67%
Test case Rework | 1 | 1 | 1 | 0% | 0%
Testing | 2 | 2 | 3 | 0% | 50%
Acceptance | 1 | 1 | 1 | 0% | 0%
Support | 1 | 1 | 1 | 0% | 0%
Project Management | 7 | 7 | 7 | 0% | 0%
PPQA (Audits) | 2 | 3 | 4 | 50% | 33.33%
Risk Mgmt | 1 | 2 | 3 | 100% | 50%
Config Mgmt | 1 | 1 | 1 | 0% | 0%
Others (DAR, Analysis & Resolution, Misc) | 2 | 3 | 2 | 50% | -33.33%
Effort Variance for Iteration No: <2> | 103 | 103 | 103 | 3.8439 | -0.44118
Total Effort Variance for the Project | 206 | 206 | 206 | 4.6415 | -0.052288

## Schedule Metrics
Metrics Analysis Report - Development Projects v 1.2
SCHEDULE VARIANCE
Ver. or Release No. / Phases | Planned Start Date | Revised Planned Start Date | Planned End Date | Revised Planned End Date | Actual Start Date | Actual End Date | Planned Duration (Person Days) | Planned Duration (against revised estimate) (Person days) | Actual Duration (Person Days) | % Variance (against planned) | % Variance (against revised estimate)
Iteration-1 | 2018-10-01 | 2018-10-01 | 2019-04-03 | 2019-04-03 | 2018-10-10 | 2019-04-30 | 103
Requirements | 2018-10-01 | 2018-10-01 | 2018-10-03 | 2018-10-03 | 2018-10-03 | 2019-10-03 | 3 | 2 | 3 | 0% | 50%
Requirements Review | 2018-10-02 | 2018-10-02 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2019-10-04 | 2 | 2 | 2 | 0% | 0%
Requirements Rework | 2018-10-03 | 2018-10-03 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2019-10-05 | 4 | 3 | 3 | -25% | 0%
Design | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 42 | 46 | 44 | 4.762% | -4.348%
Design Review | 2018-09-11 | 2018-09-12 | 2018-09-13 | 2018-09-14 | 2018-09-15 | 2018-09-16 | 5 | 5 | 6 | 20% | 20%
Design Rework | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 12 | 10 | 10 | -16.67% | 0%
Coding | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 8 | 8 | 7 | -12.5% | -12.5%
Code Review | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 1 | 1 | 1 | 0% | 0%
Code Rework | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 4 | 4 | 5 | 25% | 25%
Unit Testing | 2018-12-27 | 2018-12-28 | 2018-12-29 | 2018-12-29 | 2018-12-29 | 2018-12-29 | 3 | 3 | 3 | 0% | 0%
Unit test case Review | 2018-12-28 | 2018-12-28 | 2018-12-29 | 2018-12-30 | 2018-12-29 | 2018-12-29 | 1 | 1 | 1 | 0% | 0%
Test case Design | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | 3 | 3 | 3 | 0% | 0%
Test case Review | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 4 | 4 | 5 | 25% | 25%
Test case Rework | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 1 | 1 | 1 | 0% | 0%
Testing | 2019-01-10 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 5 | 5 | 6 | 20% | 20%
Acceptance | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 2019-01-16 | 4 | 4 | 2 | -50% | -50%
Support | [6 empty] | 1 | 1 | 1 | 0% | 0%
Schedule Variance for Iteration-1 | [6 empty] | 103 | 103 | 103 | -9.405% | 73.15%
Iteration-2
Requirements | 2018-02-01 | 2018-02-02 | 2018-02-03 | 2018-02-04 | 2018-02-05 | 2018-02-06 | 3 | 3 | 3 | 0% | 0%
Requirements Review | 2018-02-02 | 2018-02-03 | 2018-02-04 | 2018-02-05 | 2018-02-06 | 2018-02-07 | 2 | 3 | 2 | 0% | -33.33%
Requirements Rework | 2018-02-03 | 2018-02-04 | 2018-02-05 | 2018-02-06 | 2018-02-07 | 2018-02-08 | 4 | 3 | 6 | 50% | 100%
Design | 2018-03-04 | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 40 | 44 | 43 | 7.5% | -2.273%
Design Review | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-10 | 2 | 2 | 2 | 0% | 0%
Design Rework | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-10 | 2018-03-11 | 12 | 12 | 12 | 0% | 0%
Coding | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 8 | 7 | 7 | -12.5% | 0%
Code Review | 2018-04-06 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 1 | 2 | 2 | 100% | 0%
Code Rework | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 5 | 4 | 2 | -60% | -50%
Unit Testing | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 5 | 3 | 3 | -40% | 0%
Unit test case Review | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 3 | 2 | 3 | 0% | 50%
Test case Design | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 3 | 3 | 3 | 0% | 0%
Test case Review | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 5 | 6 | 7 | 40% | 16.67%
Test case Rework | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 3 | 1 | 1 | -66.67% | 0%
Testing | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 4 | 6 | 5 | 25% | -16.67%
Acceptance | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 1 | 1 | 1 | 0% | 0%
Support | 5: 2; 6: 1; 7: 1; 40%: -5000%; 16.67%: 0%
Schedule Variance for Iteration-2 | 5: 103; 6: 103; 7: 103
Total Schedule Variance for the Project | 5: 206; 6: 206; 7: 206
Note on B6: Format : dd-mmm-yyyy

## Defects Metrics
Metrics Analysis Report - Development Projects v 1.2
Review Effectiveness
| No. of Reviews Iteration No. <<1>> | No. of Reviews Iteration No. <<2>>
Requirements | 20 | 12
Design | 10 | 2
Coding | 3 | 0
Testing | 0 | 0
Documentation | 0 | 1
Support | 0 | 0
Others (DAR, Analysis & Resolution, Misc) | 0 | 0
Total number of Defects | 33 | 15
SIZE VARIANCE
Version / Release No. | Estimated Size (size units) | Actual Size (size units)
Iteration No. <<1>> | 15 | 16
Iteration No. <<2>> | 15 | 16
DEFECT DENSITY
Phase/Iteration | No. of Defects Iteration No. <<1>> | No. of Defects Iteration No. <<2>>
Requirements | 5 | 3
Design | 2 | 0
Coding | 4 | 0
Testing | 3 | 0
Note on B6: Review Defects
Note on C6: Review Defects
Note on B17: Estimated effort / Total no.of requirements
Note on C17: Planned effort / Total no.of requirements
Note on B23: Reviews+Testing Defects
Note on C23: Reviews+Testing Defects

## Requirements Metrics
Metrics Analysis Report - Development Projects v 1.2
Requirements stability index
Requirements | Iteration No. <<1>> | Iteration No. <<2>> | Total No of Requirements
Baselined | 3 | 3 | 6
Added-Customer | 1 | 0 | 1
Added-Internal | 0 | 0 | 0
Deleted | 0 | 0 | 0
Changed | 1 | 0 | 1
RS Index | 0.33333 | 1 | 0.66667
Note on A7: Number of initial requirements
Note on A8: Number of requirements added by customer
Note on A9: Number of requirements added internally by project manager
Note on A10: Number of requirements deleted
Note on A11: Number of requirements changed

## Customer Metrics
Metrics Analysis Report - Development Projects v 1.3
Project Objective: Customer Satisfaction Rating
Period | Feedback Date | Overall Feedback Rating
Q3-2018 | 2018-09-27 | 4
Q4-2018 | 2018-12-05 | 4
Q1-2019 | 2019-03-12 | 4.5
Note on A6: Quarter/Year (QxYyyyy)

## Metrics Report
Metrics Analysis Report - Development Projects v 1.0
Schedule Variance
Phase/Iterations | Iteration1 | Iteration2 | LSL | USL | Analysis
Requirements | 50% | 66.67% | -10% | 10%
Design | 15.65% | -2.273% | -10% | 10%
Coding | 12.5% | -50% | -10% | 10%
Unit Testing | 0% | 50% | -10% | 10%
Test case Design | 25% | 16.67% | -10% | 10%
Testing | 20% | -16.67% | -10% | 10%
Acceptance | -50% | 0% | -10% | 10%
Support | 0% | 0% | -10% | 10%
| 73.15% | 64.39%
Schedule Variance | 137.5%
Customer Satisfaction Rating
Period | Overall Rating | LSL | USL | Analysis
Q3-2018 | 4 | 1 | 5
Q4-2018 | 4 | 1 | 5
Q1-2019 | 4.5 | 1 | 5
Review Effectiveness
Phase | Iteration No. <<1>> |  | Iteration No. <<2>> |  | Overall
| No. of Reviews | Review Effectiveness | No. of Reviews | Review Effectiveness | Total no. of Reviews | Review Effectiveness | Analysis
Requirements | 20 | 60.6061 | 12 | 80 | 32 | 66.6667
Design | 10 | 30.303 | 2 | 13.3333 | 12 | 25
Coding | 3 | 9.0909 | 0 | 0 | 3 | 6.25
Testing | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 1 | 6.6667 | 1 | 2.0833
Support | 0 | 0 | 0 | 0 | 0 | 0
Others (DAR, Analysis & Resolution, Misc) | 0 | 0 | 0 | 0 | 0 | 0
Total number of Defects | 33 |  | 15 |  | 48
SIZE VARIANCE
Version / Release No. | Estimated Size (size units) | Actual Size (size units) | Average Size Variance % | LSL | USL | Analysis
Iteration No. <<1>> | 15 | 16 | 3.2258 | -20 | 20
Iteration No. <<2>> | 15 | 16 | 3.2258 | -20 | 20
DEFECT DENSITY
Phase/Iteration | Iteration No. <<1>> |  | Iteration No. <<2>> |  | LSL | USL | Analysis
| No. of Defects | Defect Density (Defects / Size Unit) | No. of Defects | Defect Density (Defects / Size Unit)
Requirements | 5 | 0.33333 | 3 | 0.2 | 0.01 | 0.05
Design | 2 | 0.13333 | 0 | 0 | 0.01 | 0.05
Coding | 3 | 0.2 | 0 | 0 | 0.01 | 0.05
Note on F7: Specify the Lower & Upper Specification limits
Note on B26: Quarter/Year (QxYyyyy)
Note on D26: Specify the Lower & Upper Specification limits
Note on C43: Reviews+Testing Defects
Note on E43: Reviews+Testing Defects
Note on G43: Reviews+Testing Defects
Note on G56: Specify the Lower & Upper Specification limits
Note on H63: Specify the Lower & Upper Specification limits

## ProjectData-GraphicalView (hidden)
PROJECT METRICS - GRAPHICAL VIEW
Within Iteration - Against Planned
Iterations | Requirements | Requirements Review | Requirements Rework | Design | Design Review | Design Rework | Coding | Code Review | Code Rework | Unit Testing | Unit test case Review | Test case Design | Test case Review | Test case Rework | Testing | Testing Rework | Acceptance | Project Management | PPQA (Audits) | Risk Mgmt | Config Mgmt | Others (DAR, Analysis & Resolution, Misc)
Iteration 1 | 0 | 0 | -0.25 | 0.047619 | 0.2 | -0.16667 | -0.125 | 0 | 0.25 | 0 | 0 | 0 | 0.25 | 0 | 0.2 | #REF! | -0.5 | #REF! | #REF! | #REF! | #REF! | #REF!
Iteration 2 | 0 | 0 | 0.5 | 0.075 | 0 | 0 | -0.125 | 1 | -0.6 | -0.4 | 0 | 0 | 0.4 | -0.66667 | 0.25 | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
UCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
LCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Within Iteration - Against Revised Plan (Schedule)
Iterations | Requirements | Requirements Review | Requirements Rework | Design | Design Review | Design Rework | Coding | Code Review | Code Rework | Unit Testing | Unit test case Review | Test case Design | Test case Review | Test case Rework | Testing | Testing Rework | Acceptance | Project Management | PPQA (Audits) | Risk Mgmt | Config Mgmt | Others (DAR, Analysis & Resolution, Misc)
Iteration 1 | 0.5 | 0 | 0 | -0.043478 | 0.2 | 0 | -0.125 | 0 | 0.25 | 0 | 0 | 0 | 0.25 | 0 | 0.2 | #REF! | -0.5 | #REF! | #REF! | #REF! | #REF! | #REF!
Iteration 2 | 0 | -0.33333 | 1 | -0.022727 | 0 | 0 | 0 | 0 | -0.5 | 0 | 0.5 | 0 | 0.16667 | 0 | -0.16667 | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
UCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
LCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Within Iteration - Against Planned
Iterations | Requirements | Requirements Review | Requirements Rework | Design | Design Review | Design Rework | Coding | Code Review | Code Rework | Unit Testing | Unit test case Review | Test case Design | Test case Review | Test case Rework | Testing | Testing Rework | Acceptance | Project Management | PPQA (Audits) | Risk Mgmt | Config Mgmt | Others (DAR, Analysis & Resolution, Misc)
Iteration 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Iteration 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
UCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
LCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Within Iteration - Against Revised Planned(Effort)
Iterations | Requirements | Requirements Review | Requirements Rework | Design | Design Review | Design Rework | Coding | Code Review | Code Rework | Unit Testing | Unit test case Review | Test case Design | Test case Review | Test case Rework | Testing | Testing Rework | Acceptance | Project Management | PPQA (Audits) | Risk Mgmt | Config Mgmt | Others (DAR, Analysis & Resolution, Misc)
Iteration 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Iteration 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
UCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
LCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Defect Metrics
Phase | Iteration No. <<1>> | Iteration No. <<2>> | Iteration No. <<3>> | Total No of Defects
Requirements | 20 | 12 | #REF! | 0
Design | 10 | 2 | #REF! | 0
Coding | 3 | 0 | #REF! | 0
Testing | 0 | 0 | #REF! | 0
Documentation | 0 | 1 | #REF! | 0
Others (DAR, Analysis & Resolution, Misc) | 0 | 0 | #REF! | 0
Total number of Defects | 33 | 15 | #REF! | 0