## Version History
Metrics Analysis Report - Maintenance Projects v 1.3
Sl. No. | Version No | Date | Prepared by | Reviewed by | Reviewed On | Approved by | Approved on | Change Details
1 | 1.1
Classification: TANVIIT¦ CONFIDENTIAL/INTERNAL/PUBLIC
Copyright Information The information contained in this document is the exclusive property of TanviIT Solutions Inc. This Project /Work is protected and no part of this Project /Work may be reproduced or transmitted in any form or by any means, electronic or mechanical, including photocopying and recording, or by any information storage or retrieval system, except as expressly permitted in writing by TanviIT Solutions Inc.

## Project Profile
Metrics Analysis Report - Maintenance Projects v 1.1
Project Name | Red Turf
Project Code | RT001
Team Lead | Monalisha Mishra
Project Manager | Nagoor Inaganti
Project Start Date | 2018-10-01
Project tentative end date | 2019-04-30

## Defects Metrics
Metrics Analysis Report - Maintenance Projects v 1.0
Project Objective: Defect Metrics
Severity/Status | New | Assigned | Invalid | Verified | Closed | Total No of Defects
Blocker | 1 | 0 | 1 | 2 | 3 | 7
High | 2 | 1 | 2 | 1 | 2 | 8
Medium | 1 | 2 | 2 | 3 | 1 | 9
Low | 1 | 1 | 1 | 2 | 0 | 5
Total | 5 | 4 | 6 | 8 | 6 | 29

## Schedule Metrics
Metrics Analysis Report - Maintenance Projects v 1.0
Project Objective: Releases completed on time
Month | Releases Planned | Releases Completed on Time | Variance%
2018-12-05 | 2018-12-12 | 2018-12-13 | -0.002302%
2019-03-12 | 2019-03-14 | 2019-03-15 | -0.002297%
Project Objective: Variance in WR response time
Month | Total No of WR received | Total No of WR closed | Variance%
2018-12-05 | 2018-12-12 | 2018-12-13 | -0.002302%
2019-03-12 | 2019-03-14 | 2019-03-15 | -0.002297%

## Effort Metrics
Metrics Analysis Report - Maintenance Projects v 1.0
Project Objective: Release Effort Variance
Month | Planned WR effort | Actual WR effort | Variance%
2018-12-01 | 1402 | 1428 | 1.854%
2019-03-01 | 1392 | 1402 | 0.7184%
2019-06-01 | 1394 | 1428 | 2.439%
Note on B6: Effort in person hours for all the WR's
Note on C6: smalla01: Effort in person hours for all the WR's

## Customer Metrics
Metrics Analysis Report - Maintenance Projects v 1.0
Project Objective: Customer Satisfaction Rating
Period | Feedbck Date | Overall Feedback Rating
Q32018 | 2018-09-24 | 4
Q42018 | 2018-12-26 | 4
Q12019 | 2019-03-24 | 4.5
Q22019 | 2019-07-04 | 4.5
Note on A6: Quarter/Year (QxYyyyy)

## Metrics Report
Metrics Analysis Report - Maintenance Projects v 1.0
Schedule Variance
% Releases completed on Time
Month | % Releases completed on Time | LSL | USL | Analysis
2018-12-05 | -0.002302% | -10% | 10%
2019-03-12 | -0.002297% | -10% | 10%
Schedule Variance | -0.004599%
Variance in WR response time
Month | % Releases completed on Time | LSL | USL | Analysis
2018-12-05 | -0.002302% | -10% | 10%
2019-03-12 | -0.002297% | -10% | 10%
Schedule Variance | -0.004599%
Effort Variance
Month | Effort Variance | LSL | USL | Analysis
2018-12-01 | 1.854% | -15% | 15%
2019-03-01 | 0.7184% | -15% | 15%
2019-06-01 | 2.439% | -15% | 15%
Effort Variance | 2.573%
Customer Satisfaction Rating
Period | Overall Rating | LSL | USL | Analysis
2018-09-24 | 4 | 1 | 5
2018-12-26 | 4 | 1 | 5
2019-03-24 | 4.5 | 1 | 5
2019-07-04 | 4.5 | 1 | 5
Defects Metrics
Severity/Status | New | Assigned | Invalid | Verified | Closed | Total No of Defects | Analysis
Blocker | 1 | 0 | 1 | 2 | 3 | 7
High | 2 | 1 | 2 | 1 | 2 | 8
Medium | 1 | 2 | 2 | 3 | 1 | 9
Low | 1 | 1 | 1 | 2 | 0 | 5
Note on E7: Specify the Lower & Upper Specification limits
Note on E13: Specify the Lower & Upper Specification limits
Note on E24: Specify the Lower & Upper Specification limits
Note on B33: Quarter/Year (QxYyyyy)
Note on E33: Specify the Lower & Upper Specification limits