## Version History
Metrics Analysis Report - Quality v 1.3
Sl. No. | Version No | Date | Prepared by | Reviewed by | Reviewed On | Approved by | Approved on | Change Details
1 | 1.1 | 2018-10-10 | Nagoor Inaganti | Nagoor Inaganti | 2018-10-10 | Nagoor Inaganti | 2018-10-10
2 | 1.2 | 2018-12-24 | Nagoor Inaganti | Nagoor Inaganti | 2018-12-24 | Nagoor Inaganti | 2018-12-24 | Updated report
3 | 1.3 | 2019-03-24 | Nagoor Inaganti | Nagoor Inaganti | 2019-03-24 | Nagoor Inaganti | 2019-03-24 | Updated report
Classification: TANVIIT¦ CONFIDENTIAL/INTERNAL/PUBLIC
Copyright Information The information contained in this document is the exclusive property of TanviIT Solutions Inc. This Project /Work is protected and no part of this Project /Work may be reproduced or transmitted in any form or by any means, electronic or mechanical, including photocopying and recording, or by any information storage or retrieval system, except as expressly permitted in writing by TanviIT Solutions Inc.

## SQA Metrics Sheet
Metrics Analysis Report - Quality v 1.3
| 2018-10-18 | 2018-12-18 | 2019-03-19
No of SQA Reviews Planned | 2 | 2 | 2
No of SQA Reviews Conducted | 2 | 2 | 2
No of NCs/ Findings | 2 | 2 | 2
Actual
Objective: | 2018-10-18 | 2018-12-18 | 2019-03-19
Number of SQA Audits to be conducted each month: >=2 | 2 | 2 | 2
Number of NCs/ Findings per audit:=> 2 | 2 | 2 | 2

## Metrics Analysis Report-Quality
Metrics Analysis Report - Quality v 1.3
Prepared By: | Nagoor Inaganti
Updated on: | 2019-03-24
Month | Count for approved CRs | CR No (QMS Request Id) | CR approved for implementation on date | Change released on date | QMS Released within a month ? (0-Yes, 1-No) | % Service Level | Remarks
2018-10-10 | 3 | 3 | 2018-10-24 | 2018-10-26 | 0 | 100
0
0
OCT TOTAL | 1 |  |  |  | 0 | 100
2018-12-24 | 1 | 1 | 2018-12-27 | 2018-12-28 | 0 | 100
0
0
DEC TOTAL | 1 |  |  |  | 0 | 100
2019-03-24 | 2 | 2 | 2019-03-12 | 2019-03-15 | 0
0
0
MAR TOTAL | 1 | NA | NA | NA | 0 | 100
Metrics Details |  |  | 2018-10-10 | 2018-12-24 | 2019-03-12
QMS Approved Change Requests Received |  |  | 3 | 1 | 2
QMS Requests Scheduled for Completion |  |  | 3 | 1 | 2
QMS Changes Completed |  |  | 3 | 1 | 2
Project Objectives Achievements Summary |  |  | 2018-10-10 | 2018-12-24 | 2019-03-12
% Service Level for QMS Changes (Addressing the Change requests within 30 Days from Approval) |  |  | 100 | 100 | 100
Quality Objective Target |  |  | >=90% | >=90% | >=90%
Note on D8: smanne: CR final approval along with changes incorporated in QMS documents
Note on E8: smanne: Release Note Date

## Quality Training DataCollection
Metrics Analysis Report - Quality v 1.3
Month | Sl No | Training Request (TR) details | TR approved for implementation on date | Training done on date | Training done within 15 Days ? (0-Yes, 1-No) | % Service Level | Remarks
2018-10-10 | 2 | 2 | 2018-10-24 | 2018-10-26 | 0 | 100
0
0
OCT TOTAL | 1 |  |  |  | 0 | 100
2018-12-24 | 1 | 1 | 2018-12-27 | 2018-12-28 | 0 | 100
0
0
DEC TOTAL | 1 |  |  |  | 0 | 100
2019-03-24 | 0 | 0 | 2019-03-12 | 2019-03-15 | 0
0
0
MAR TOTAL | 1 | NA | NA | NA | 0 | 100
Metrics Details |  |  | 2018-10-10 | 2018-12-24 | 2019-03-12
Training Requests Received |  |  | 3 | 1 | 2
Training Requests Scheduled for Completion |  |  | 3 | 1 | 2
Trainings Completed |  |  | 3 | 1 | 2
Project Objectives Achievements Summary is Given Below
Metrics item |  | MMM-YY | MMM-YY | MMM-YY
% Service Level |  | 100 | 100 | 100
Quality Objective Target |  | >=90% | >=90% | >=90%